## AGILE SCOPING
SCOPE/Themes | User Type |  | Epic | User Story | Comments | Status to task
The users receives up-to-date information from stock-markets(securities and exchange) and crypto-currencies, on either a daily basis or weekly basis that is in relative to a user's personal portfolio. The users will receive news and other articles and links to additional information that relate to each individual listed security in their news-feed, and a digest of articles will appear on the index page for the general public. The users can add additional APIs from other websites and store the links under their profile. The users can receive an email that that provide the latest updates available for the securities listed in their portfolio. | Tech User | EPIC1 | Epic 1-a Registration | 1-As a vistor, I can sign-up to the app as a new user so I can access additional features | CAPTCHA BOT
As a visitor who had just registered, I will receive a confirmation email once I have registered for the application
|  |  | Epic 1-b Login | As a user I can log into the application by entering my email and password
As a user I want to be able to reset my password if I have forgotten my password
|  |  | Epic 1-c My account | As a user, I can view my personal information | Add cookies
|  |  |  | as a user I want to update my email , I want to receive confirmation email to my new email address | email
as a user I would like to receive updates via an API
|  |  |  | They may also retrieve the latest available visual snapshot for the market data of any stock if the data is available via the API and the website | API Wrapping to call another API
|  |  |  | as a user I want to subscribe to email notifications | each user may define a portfolio of stocks they subscribe to.
as a user I want to un-subscribe to email notifications
as a user I want to delete my account
|  |  |  | as a user I want to select the frequency of updates, either daily or weekly. | Both kinds of users may define the frequency of the updates, whether they are daily or weekly.
as a user I want to re-generate an API key
as a user I want to interact with the website via a dashboard
as a user I want to toggle the dashboard on and off
As a user I want to log out of my account
Epic 1-e Dashboard
|  |  | Epic 2-a Registration | as a user I want to see a new feed on my dashboard based on my selected portfolio
| Non Technical User | Epic2 |  | 1-As a vistor, I can sign-up to the app as a new user so I can access additional features
As a visitor who had just registered, I will receive a confirmation email once I have registered for the application
Epic-2b Login
As a user I can log into the application by entering my email and password
As a user I want to be able to reset my password if I have forgotten my password
Epic-2c My account
As a user, I can view my personal information
as a user I can update my email , I will receive confirmation email to my new email addres
|  |  |  | as a user I want to subscribe to email notifications | ability to choose options to add to my portfolio
as a user I want to un-subscribe to email notifcaitons
as a user I would like to receive updates via an API
They may also retrieve the latest available visual snapshot for the market data of any stock if the data is available via the API and the website
as a user I can toggle the dashboard on and off
As a user I can log out of my account
Epic-2e Dashboard
Epic 3 Home page news feed
as a user I want to see a news feed on my dashboard based on my selected portfolio
| Epic 3 Visitor to the site - | Epic 3 |  | as a user I want to read the latest news/articles/digest on the main website

## User stories
# | User Story | Acceptance Criteria | Notes/dependencies This will be discussed in something called Sprint Planning. Sprint planning is an event in scrum that kicks off the sprint. The purpose of sprint planning is to define what can be delivered in the sprint and how that work will be achieved. Sprint planning is done in collaboration with the whole scrum team | TASKS: Keep your tasks small!!!!
1-Registration | 1-As a vistor, I can sign-up to the app as a new user so I can access additional features | Scenario: Visitor registers with valid credentials “Given I’m a unregistered guest user and I’m on the home page' When I click the sign-up/login button , fill in the "username" , “email address” , a valid 8 digit “Password” & "Confirm password", click on the CAPTCHA BOT AND: I click the submit/register/create account button. Then the system displays a pop up message about checking my emails" | Base Website Signup/Login Database??? £ | install and learn flask Mysql -Database design tables, columns for user registration. Both to create new env for project Home Page SignUp/Login | Registration : *UserName *Password *email address (can be used again) Login: *email address (can be used again) *Password Eugene: Database creation Research connection to Link from site to db -Methods for db -DB connection -write(INSERT) into db/table Both to check session management??? Kaylyn: To create main.py file Index.html file to site Upload to Github -Method to read from db -read(SELECT) from db.
| As a visitor who had just registered, I will receive a confirmation email once I have registered for the application | Scenario: Newly registered visitor "Given that I am a newly registered user" “When i clicked on the create account/submit button and have seen the pop up msg, Then I will receive an email to the email address which I have registered with confirming the registration of my account | Email method
2-Login/Logout | As a user I can log into the application by entering my email and password | Scenario: Logged out user on the "sign up" page attempts to signup “Given that i enter an email address that is already associated with a user and a valid password' When I click the sign-up , Then: the system notifies me that the email address has already been taken.
| As a user I want to be able to reset my password if I have forgotten my password | Scenario: Registered user attempts to login but cannot remember password. "Given that I cannot remember my password, When I click the sign-up button, Then: the system allows me to reset my password | How will this be done? Email to reset password via another link? Answer a secret question? Simple=better(cost/time saving, can always expand)
| As a user, I want to know if I already have an account on the app when I try to sign-up, so I can use the login page instead | Scenario: Logged out user on the "sign up" page attempts to signup “Given that i enter an email address that is already associated with a user and a valid password' When I click the sign-up button , Then: the system notifies me that the email address has already been taken.
| As a logged out user, I want to log in securely so I can access the application's features and my data in a protected way. | Scenario: Logged out user tries to log in with valid credentials “Given : that i am a logged out user and am on the login page,' When : I fill in the 'Email' and 'Password' fields with my valid authentication info Then: the system logs me in AND : I am navigated to my dashboard''
| As a logged out user, I want to log in securely so I can access the application's features and my data in a protected way. | Scenario: Logged out user tries to log in within valid email or password “Given : that i am a logged out user and am on the login page,' When : I fill in the 'Email' and 'Password' fields with an invalid email and/or password Then: the system logs notifies me with an error message that this email or password is incorrect AND : I stay on the login page''
3
4
5

## User story Template & Guide
Name | User story: | Key words
Sign-in | As a logged-out user I want to be able to sign in to a website So that I can find acess my personal profile
As a
I want
So that
Acceptance criteria for that user story could be:
Scenario: System user signs in with valid credentials “Given I’m a logged-out system user and I’m on the Sign-In page When I fill in the “Username” and “Password” fields with my authentication credentials and I click the Sign-In button Then the system signs me in”
Scenario
Given that
when i
then
Sites with examples
https://coda.io/@tom-gauthier/p3-designez-une-application/user-stories-acceptance-criteria-8
https://mentormate.com/blog/how-user-stories-technical-tasks-elevate-software-projects/
Things to Note:
Tasks shouldn't take more than a day There are several reasons that experts recommend this: Daily tasks would match the cadence of the daily stand-up. By having tasks that take a day or less, progress (or lack thereof) is clear at the daily stand-up meeting. Daily tasks increase the transparency of what everyone on the team is working on. The team is able to inspect and adapt daily. Limiting tasks to a day or less can help developers create flow, with focused, uninterrupted time.

## Resource Links
Resources
r-g-r cycle: | https://www.youtube.com/watch?v=EZ05e7EMOLM
triangulation: | https://www.tddfellow.com/blog/2016/08/31/getting-stuck-while-doing-tdd-part-3-triangulation-to-the-rescue/
progression: | https://8thlight.com/blog/georgina-mcfadyen/2016/06/27/inside-out-vs-outside-in.html
integration testing: | https://martinfowler.com/bliki/IntegrationTest.html
travis ci: | https://docs.travis-ci.com/user/tutorial/
daily builds: | https://joelonsoftware.com/2001/01/27/daily-builds-are-your-friend/
source controls: | https://docs.github.com/en/github/collaborating-with-issues-and-pull-requests/about-pull-request-reviews
product backlog | https://tech.gsa.gov/guides/#Agile
pull requests: | https://blog.hyperiondev.com/index.php/2018/10/10/what-does-it-mean-to-become-a-code-reviewer/
HTML Templates | https://themewagon.com/loginsign-up-form-to-compliment-your-website/
Sample website code | https://codepen.io/
HTML Templates | https://www.template.net/web-templates/htmlcss-templates/signup-form/
HTML Templates | https://colorlib.com/wp/templates/
SSL | https://dash.cloudflare.com/login