## Sheet1
Date: | Task at hand | Person | Outcome | NOTES
2022-10-08 | Github project file create | K | Completed 2022/10/08
2022-10-08 | Dropbox folder create | E | Completed 2022/10/08
2022-10-08 | Draw.io download | K
2022-10-08 | Trello Board profile create | K | Completed 2022/10/08
2022-10-08 | Web-server Information gathering | E | Completed 2022/10/08 | Free web hosting and scrapers.xlsx
2022-10-08 | Languages Information gathering | C
2022-10-08 | Online Security | E | Completed 2022/10/08 | Sorted by website hosting service
2022-10-08 | Postman profile creation | E | Completed 2022/10/08
2022-10-08 | Find web-scraping tools | E | Completed 2022/10/08 | Free web hosting and scrapers.xlsx
2022-10-09 | Check out Python anywhere | E
2022-10-09 | Checkout TyWeb.io | E
2022-10-09 | Checkout Heroku | E
2022-10-09 | Develop user requirements + user stories | E
2022-10-09 | Work on user stories | K
2022-10-09 | Do task breakdown | K
2022-10-09 | Get project planner and templates | K
2022-10-09
2022-10-09